## Take Off
[11 empty] | Face View |  |  |  |  | Sheet Size | [5 empty] | Materials
Ref. | TQ/PR | Project Name | Product | Description | Drawing | Level | Elev. | Prod. | Colour | PPC Side | Height | Width | Qty | Total LM | Total M2 | Height | Width | Qty | Toal LM | Total M2 | Unit | Thickness | Type | Welds | Comments | Weight | Phase | Priority 1
1 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-01 470x1105 (Girth 631 x 1241) | CSS-P1-PB1 | PB1-01 | South | (L2-6) | Bronze: 56PRR/4163 | Outside | 470 | 1105 | 2 | 2.21 | 1.0387 | 631 | 1241 | 2 | 2.482 | 1.5661 | m2 | 3 | Alu. |  | 9 | 12.6858 | 1 | 1
2 | PR2306 (SO-777) | Chapel Street | Stiffener | Stiffener PB1-01 50x1105 (Girth 198 x 1105) | CSS-P1-PB1 | PB1-01 | South | (L2-6) | Mill Finish | Outside | 50 | 1105 | 2 | 2.21 | 0.1105 | 198 | 1105 | 2 | 2.21 | 0.43758 | m2 | 3 | Alu. |  | 9 | 3.5444 | 1 | 1
3 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-02 470x907 (Girth 631 x 1043) | CSS-P1-PB1 | PB1-02 | South | (L2-6) | Bronze: 56PRR/4163 | Outside | 470 | 907 | 2 | 1.814 | 0.85258 | 631 | 1043 | 2 | 2.086 | 1.3163 | m2 | 3 | Alu. |  | 2 | 10.6618 | 1 | 1
4 | PR2306 (SO-777) | Chapel Street | Stiffener | Stiffener PB1-02 50x907 (Girth 198 x 907) | CSS-P1-PB1 | PB1-02 | South | (L2-6) | Mill Finish | Outside | 50 | 907 | 2 | 1.814 | 0.0907 | 198 | 907 | 2 | 1.814 | 0.35917 | m2 | 3 | Alu. |  | 2 | 2.9093 | 1 | 1
5 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-03 470x280 (Girth 631 x 416) | CSS-P1-PB1 | PB1-03 | South | (L2-6) | Bronze: 56PRR/4163 | Outside | 470 | 280 | 2 | 0.56 | 0.2632 | 631 | 416 | 2 | 0.832 | 0.52499 | m2 | 3 | Alu. |  | 6 | 4.2524 | 1 | 1
6 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-07 2855x907 (Girth 3016 x 1043) | CSS-P1-PB1 | PB1-07 | South | (L2-6) | Bronze: 56PRR/4163 | Outside | 2855 | 907 | 10 | 9.07 | 25.8949 | 3016 | 1043 | 10 | 10.43 | 31.4569 | m2 | 3 | Alu. |  | 10 | 254.8007 | 1 | 1
7 | PR2306 (SO-777) | Chapel Street | Stiffener | Stiffener PB1-07 50x907 (Girth 198 x 907) | CSS-P1-PB1 | PB1-07 | South | (L2-6) | Mill Finish | Outside | 50 | 907 | 40 | 36.28 | 1.814 | 198 | 907 | 40 | 36.28 | 7.1834 | m2 | 3 | Alu. |  | 40 | 58.1859 | 1 | 1
8 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-03 470x280 (Girth 631 x 416) | CSS-P1-PB1 | PB1-03 | West | (L2-6) | Bronze: 56PRR/4163 | Outside | 470 | 280 | 3 | 0.84 | 0.3948 | 631 | 416 | 3 | 1.248 | 0.78749 | m2 | 3 | Alu. |  | 3 | 6.3787 | 1 | 1
9 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-30 470x1011 (Girth 631 x 1147) | CSS-P1-PB1 | PB1-30 | West | (L2-6) | Bronze: 56PRR/4163 | Outside | 470 | 1011 | 5 | 5.055 | 2.3758 | 631 | 1147 | 5 | 5.735 | 3.6188 | m2 | 3 | Alu. |  | 5 | 29.3122 | 1 | 1
10 | PR2306 (SO-777) | Chapel Street | Stiffener | Stiffener PB1-30 50x1011 (Girth 198 x 1011) | CSS-P1-PB1 | PB1-30 | West | (L2-6) | Mill Finish | Outside | 50 | 1011 | 5 | 5.055 | 0.25275 | 198 | 1011 | 5 | 5.055 | 1.0009 | m2 | 3 | Alu. |  | 5 | 8.1072 | 1 | 1
11 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-33 470x639 (Girth 631 x 775) | CSS-P1-PB1 | PB1-33 | West | (L2-6) | Bronze: 56PRR/4163 | Outside | 470 | 639 | 1 | 0.639 | 0.30033 | 631 | 775 | 1 | 0.775 | 0.48902 | m2 | 3 | Alu. |  | 1 | 3.9611 | 1 | 1
12 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-08 2855x280 (Girth 3016 x 416) | CSS-P1-PB1 | PB1-08 | West | (L2-6) | Bronze: 56PRR/4163 | Outside | 2855 | 280 | 15 | 4.2 | 11.991 | 3016 | 416 | 15 | 6.24 | 18.8198 | m2 | 3 | Alu. |  | 15 | 152.4407 | 1 | 1
13 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-31 2855x1011 (Girth 3016 x 1147) | CSS-P1-PB1 | PB1-31 | West | (L2-6) | Bronze: 56PRR/4163 | Outside | 2855 | 1011 | 25 | 25.275 | 72.1601 | 3016 | 1147 | 25 | 28.675 | 86.4838 | m2 | 3 | Alu. |  | 25 | 700.5188 | 1 | 1
14 | PR2306 (SO-777) | Chapel Street | Stiffener | Stiffener PB1-31 50x1011 (Girth 198 x 1011) | CSS-P1-PB1 | PB1-31 | West | (L2-6) | Mill Finish | Outside | 50 | 1011 | 100 | 101.1 | 5.055 | 198 | 1011 | 100 | 101.1 | 20.0178 | m2 | 3 | Alu. |  | 100 | 162.1442 | 1 | 1
15 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-34 2855x639 (Girth 3016 x 775) | CSS-P1-PB1 | PB1-34 | West | (L2-6) | Bronze: 56PRR/4163 | Outside | 2855 | 639 | 5 | 3.195 | 9.1217 | 3016 | 775 | 5 | 3.875 | 11.687 | m2 | 3 | Alu. |  | 5 | 94.6647 | 1 | 1
16 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-07 2855x907 (Girth 3016 x 1043) | CSS-P2-PB1 | PB1-07 | South | (L7-10) | Bronze: 56PRR/4163 | Outside | 2855 | 907 | 8 | 7.256 | 20.7159 | 3016 | 1043 | 8 | 8.344 | 25.1655 | m2 | 3 | Alu. |  | 8 | 203.8406 | 2 | 1
17 | PR2306 (SO-777) | Chapel Street | Stiffener | Stiffener PB1-07 50x907 (Girth 198 x 907) | CSS-P2-PB1 | PB1-07 | South | (L7-10) | Mill Finish | Outside | 50 | 907 | 32 | 29.024 | 1.4512 | 198 | 907 | 32 | 29.024 | 5.7468 | m2 | 3 | Alu. |  | 32 | 46.5487 | 2 | 1
18 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-08 2855x280 (Girth 3016 x 416) | CSS-P2-PB1 | PB1-08 | West | (L7-10) | Bronze: 56PRR/4163 | Outside | 2855 | 280 | 12 | 3.36 | 9.5928 | 3016 | 416 | 12 | 4.992 | 15.0559 | m2 | 3 | Alu. |  | 12 | 121.9526 | 2 | 1
19 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-31 2855x1011 (Girth 3016 x 1147) | CSS-P2-PB1 | PB1-31 | West | (L7-10) | Bronze: 56PRR/4163 | Outside | 2855 | 1011 | 20 | 20.22 | 57.7281 | 3016 | 1147 | 20 | 22.94 | 69.187 | m2 | 3 | Alu. |  | 20 | 560.415 | 2 | 1
20 | PR2306 (SO-777) | Chapel Street | Stiffener | Stiffener PB1-31 50x1011 (Girth 198 x 1011) | CSS-P2-PB1 | PB1-31 | West | (L7-10) | Mill Finish | Outside | 50 | 1011 | 80 | 80.88 | 4.044 | 198 | 1011 | 80 | 80.88 | 16.0142 | m2 | 3 | Alu. |  | 80 | 129.7153 | 2 | 1
21 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-34 2855x639 (Girth 3016 x 775) | CSS-P2-PB1 | PB1-34 | West | (L7-10) | Bronze: 56PRR/4163 | Outside | 2855 | 639 | 4 | 2.556 | 7.2974 | 3016 | 775 | 4 | 3.1 | 9.3496 | m2 | 3 | Alu. |  | 4 | 75.7318 | 2 | 1
22 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-06 377x1105 (Girth 538 x 1241) | CSS-P3-PB1 | PB1-06 | South | (L11-16) | Bronze: 56PRR/4163 | Outside | 377 | 1105 | 22 | 24.31 | 9.1649 | 538 | 1241 | 22 | 27.302 | 14.6885 | m2 | 3 | Alu. |  | 32 | 118.9767 | 3 | 1
23 | PR2306 (SO-777) | Chapel Street | Stiffener | Stiffener PB1-06 50x1105 (Girth 198 x 1105) | CSS-P3-PB1 | PB1-06 | South | (L11-16) | Mill Finish | Outside | 50 | 1105 | 22 | 24.31 | 1.2155 | 198 | 1105 | 22 | 24.31 | 4.8134 | m2 | 3 | Alu. |  | 32 | 38.9884 | 3 | 1
24 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-07 2855x907 (Girth 3016 x 1043) | CSS-P3-PB1 | PB1-07 | South | (L11-16) | Bronze: 56PRR/4163 | Outside | 2855 | 907 | 4 | 3.628 | 10.3579 | 3016 | 1043 | 4 | 4.172 | 12.5828 | m2 | 3 | Alu. |  | 4 | 101.9203 | 3 | 1
25 | PR2306 (SO-777) | Chapel Street | Stiffener | Stiffener PB1-07 50x907 (Girth 198 x 907) | CSS-P3-PB1 | PB1-07 | South | (L11-16) | Mill Finish | Outside | 50 | 907 | 16 | 14.512 | 0.7256 | 198 | 907 | 16 | 14.512 | 2.8734 | m2 | 3 | Alu. |  | 16 | 23.2743 | 3 | 1
26 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-08 2855x280 (Girth 3016 x 416) | CSS-P3-PB1 | PB1-08 | South | (L11-16) | Bronze: 56PRR/4163 | Outside | 2855 | 280 | 11 | 3.08 | 8.7934 | 3016 | 416 | 11 | 4.576 | 13.8012 | m2 | 3 | Alu. |  | 22 | 111.7898 | 3 | 1
27 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-11 465x1105 (Girth 626 x 1241) | CSS-P3-PB1 | PB1-11 | South | (L11-16) | Bronze: 56PRR/4163 | Outside | 465 | 1105 | 2 | 2.21 | 1.0276 | 626 | 1241 | 2 | 2.482 | 1.5537 | m2 | 3 | Alu. |  | 9 | 12.5852 | 3 | 1
28 | PR2306 (SO-777) | Chapel Street | Stiffener | Stiffener PB1-11 50x1105 (Girth 198 x 1105) | CSS-P3-PB1 | PB1-11 | South | (L11-16) | Mill Finish | Outside | 50 | 1105 | 2 | 2.21 | 0.1105 | 198 | 1105 | 2 | 2.21 | 0.43758 | m2 | 3 | Alu. |  | 9 | 3.5444 | 3 | 1
29 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-12 465x907 (Girth 626 x 1043) | CSS-P3-PB1 | PB1-12 | South | (L11-16) | Bronze: 56PRR/4163 | Outside | 465 | 907 | 2 | 1.814 | 0.84351 | 626 | 1043 | 2 | 2.086 | 1.3058 | m2 | 3 | Alu. |  | 2 | 10.5773 | 3 | 1
30 | PR2306 (SO-777) | Chapel Street | Stiffener | Stiffener PB1-12 50x907 (Girth 198 x 907) | CSS-P3-PB1 | PB1-12 | South | (L11-16) | Mill Finish | Outside | 50 | 907 | 2 | 1.814 | 0.0907 | 198 | 907 | 2 | 1.814 | 0.35917 | m2 | 3 | Alu. |  | 2 | 2.9093 | 3 | 1
31 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-13 465x280 (Girth 626 x 416) | CSS-P3-PB1 | PB1-13 | South | (L11-16) | Bronze: 56PRR/4163 | Outside | 465 | 280 | 1 | 0.28 | 0.1302 | 626 | 416 | 1 | 0.416 | 0.26042 | m2 | 3 | Alu. |  | 6 | 2.1094 | 3 | 1
32 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-08 2855x280 (Girth 3016 x 416) | CSS-P3-PB1 | PB1-08 | West | (L11-16) | Bronze: 56PRR/4163 | Outside | 2855 | 280 | 6 | 1.68 | 4.7964 | 3016 | 416 | 6 | 2.496 | 7.5279 | m2 | 3 | Alu. |  | 6 | 60.9763 | 3 | 1
33 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-31 2855x1011 (Girth 3016 x 1147) | CSS-P3-PB1 | PB1-31 | West | (L11-16) | Bronze: 56PRR/4163 | Outside | 2855 | 1011 | 10 | 10.11 | 28.864 | 3016 | 1147 | 10 | 11.47 | 34.5935 | m2 | 3 | Alu. |  | 10 | 280.2075 | 3 | 1
34 | PR2306 (SO-777) | Chapel Street | Stiffener | Stiffener PB1-31 50x1011 (Girth 198 x 1011) | CSS-P3-PB1 | PB1-31 | West | (L11-16) | Mill Finish | Outside | 50 | 1011 | 40 | 40.44 | 2.022 | 198 | 1011 | 40 | 40.44 | 8.0071 | m2 | 3 | Alu. |  | 40 | 64.8577 | 3 | 1
35 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-34 2855x639 (Girth 3016 x 775) | CSS-P3-PB1 | PB1-34 | West | (L11-16) | Bronze: 56PRR/4163 | Outside | 2855 | 639 | 2 | 1.278 | 3.6487 | 3016 | 775 | 2 | 1.55 | 4.6748 | m2 | 3 | Alu. |  | 2 | 37.8659 | 3 | 1
36 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-32 465x1011 (Girth 626 x 1147) | CSS-P3-PB1 | PB1-32 | West | (L11-16) | Bronze: 56PRR/4163 | Outside | 465 | 1011 | 5 | 5.055 | 2.3506 | 626 | 1147 | 5 | 5.735 | 3.5901 | m2 | 3 | Alu. |  | 5 | 29.0799 | 3 | 1
37 | PR2306 (SO-777) | Chapel Street | Stiffener | Stiffener PB1-32 50x1011 (Girth 198 x 1011) | CSS-P3-PB1 | PB1-32 | West | (L11-16) | Mill Finish | Outside | 50 | 1011 | 5 | 5.055 | 0.25275 | 198 | 1011 | 5 | 5.055 | 1.0009 | m2 | 3 | Alu. |  | 5 | 8.1072 | 3 | 1
38 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-13 465x280 (Girth 626 x 416) | CSS-P3-PB1 | PB1-13 | West | (L11-16) | Bronze: 56PRR/4163 | Outside | 465 | 280 | 2 | 0.56 | 0.2604 | 626 | 416 | 2 | 0.832 | 0.52083 | m2 | 3 | Alu. |  | 2 | 4.2187 | 3 | 1
39 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB1-35 465x639 (Girth 626 x 775) | CSS-P3-PB1 | PB1-35 | West | (L11-16) | Bronze: 56PRR/4163 | Outside | 465 | 639 | 1 | 0.639 | 0.29713 | 626 | 775 | 1 | 0.775 | 0.48515 | m2 | 3 | Alu. |  | 5 | 3.9297 | 3 | 1
40 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB2-01 470x915 (Girth 631 x 985) | CSS-P1-PB2 | PB2-01 | South | (L2-6) | Bronze: 56PRR/4163 | Outside | 470 | 915 | 1 | 0.915 | 0.43005 | 631 | 985 | 1 | 0.985 | 0.62153 | m2 | 3 | Alu. |  | 1 | 5.0344 | 1 | 1
41 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB2-04 2855x915 (Girth 3016 x 985) | CSS-P1-PB2 | PB2-04 | South | (L2-6) | Bronze: 56PRR/4163 | Outside | 2855 | 915 | 5 | 4.575 | 13.0616 | 3016 | 985 | 5 | 4.925 | 14.8538 | m2 | 3 | Alu. |  | 5 | 120.3158 | 1 | 1
42 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB2-04 2855x915 (Girth 3016 x 985) | CSS-P2-PB2 | PB2-04 | South | (L7-10) | Bronze: 56PRR/4163 | Outside | 2855 | 915 | 4 | 3.66 | 10.4493 | 3016 | 985 | 4 | 3.94 | 11.883 | m2 | 3 | Alu. |  | 4 | 96.2526 | 2 | 1
43 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB2-04 2855x915 (Girth 3016 x 985) | CSS-P1-PB2 | PB2-04 | South | (L11-16) | Bronze: 56PRR/4163 | Outside | 2855 | 915 | 2 | 1.83 | 5.2246 | 3016 | 985 | 2 | 1.97 | 5.9415 | m2 | 3 | Alu. |  | 2 | 48.1263 | 3 | 1
44 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB2-07 2880x909 (Girth 3041 x 979) | CSS-P1-PB2 | PB2-07 | South | (L11-16) | Bronze: 56PRR/4163 | Outside | 2880 | 909 | 1 | 0.909 | 2.6179 | 3041 | 979 | 1 | 0.979 | 2.9771 | m2 | 3 | Alu. |  | 1 | 24.1148 | 3 | 1
45 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB3-04 2855x1177 (Girth 3016 x 1243) | CSS-P1-PB3 | PB3-04 | South | (L2-6) | Bronze: 56PRR/4163 | Outside | 2855 | 1177 | 5 | 5.885 | 16.8017 | 3016 | 1243 | 5 | 6.215 | 18.7444 | m2 | 3 | Alu. |  | 5 | 151.83 | 1 | 1
46 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB3-04 2855x1177 (Girth 3016 x 1243) | CSS-P2-PB3 | PB3-04 | South | (L7-10) | Bronze: 56PRR/4163 | Outside | 2855 | 1177 | 4 | 4.708 | 13.4413 | 3016 | 1243 | 4 | 4.972 | 14.9956 | m2 | 3 | Alu. |  | 4 | 121.464 | 2 | 1
47 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB3-07 465x621 (Girth 626 x 687) | CSS-P2-PB3 | PB3-07 | South | (L7-10) | Bronze: 56PRR/4163 | Outside | 465 | 621 | 1 | 0.621 | 0.28876 | 626 | 687 | 1 | 0.687 | 0.43006 | m2 | 3 | Alu. |  | 1 | 3.4835 | 2 | 1
48 | PR2306 (SO-777) | Chapel Street | Panel | Panel PB3-04 2855x1177 (Girth 3016 x 1243) | CSS-P3-PB3 | PB3-04 | South | (L11-16) | Bronze: 56PRR/4163 | Outside | 2855 | 1177 | 2 | 2.354 | 6.7207 | 3016 | 1243 | 2 | 2.486 | 7.4978 | m2 | 3 | Alu. |  | 2 | 60.732 | 3 | 1
49 | PR2306 (SO-777) | Chapel Street | Corner Panel 1/2 | Corner Panel 1/2 PG&B-CNR4-2 465x190 (Girth 626 x 309) | CSS-P3-PG&B-CNR4 | PG&B-CNR4-2 | North | (L11-16) | Bronze: 56PRR/4163 | Outside | 465 | 190 | 1 | 0.19 | 0.08835 | 626 | 309 | 1 | 0.309 | 0.19343 | m2 | 3 | Alu. |  | 1 | 1.5668 | 3 | 1
50 | PR2306 (SO-777) | Chapel Street | Corner Panel 2/2 | Corner Panel 2/2 PG&B-CNR4-2 465x310 (Girth 626 x 433) | CSS-P3-PG&B-CNR4 | PG&B-CNR4-2 | North | (L11-16) | Grey: 56B0/4850 | Outside | 465 | 310 | 1 | 0.31 | 0.14415 | 626 | 433 | 1 | 0.433 | 0.27106 | m2 | 3 | Alu. |  | 1 | 2.1956 | 3 | 1
51 | PR2306 (SO-777) | Chapel Street | Panel | Panel PG1-73 755x978 (Girth 916 x 1114) | CSS-P1-PG1 | PG1-73 | West | (L2-6) | Grey: 56B0/4850 | Outside | 755 | 978 | 1 | 0.978 | 0.73839 | 916 | 1114 | 1 | 1.114 | 1.0204 | m2 | 3 | Alu. |  | 1 | 8.2654 | 1 | 1
52 | PR2306 (SO-777) | Chapel Street | Stiffener | Stiffener PG1-73 50x978 (Girth 198 x 978) | CSS-P1-PG1 | PG1-73 | West | (L2-6) | Mill Finish | Outside | 50 | 978 | 1 | 0.978 | 0.0489 | 198 | 978 | 1 | 0.978 | 0.19364 | m2 | 3 | Alu. |  | 1 | 1.5685 | 1 | 1
53 | PR2306 (SO-777) | Chapel Street | Panel | Panel PG1-74 755x566 (Girth 916 x 702) | CSS-P1-PG1 | PG1-74 | West | (L2-6) | Grey: 56B0/4850 | Outside | 755 | 566 | 1 | 0.566 | 0.42733 | 916 | 702 | 1 | 0.702 | 0.64303 | m2 | 3 | Alu. |  | 1 | 5.2086 | 1 | 1
54 | PR2306 (SO-777) | Chapel Street | Panel | Panel PG1-75 2855x566 (Girth 3016 x 702) | CSS-P1-PG1 | PG1-75 | West | (L2-6) | Grey: 56B0/4850 | Outside | 2855 | 566 | 5 | 2.83 | 8.0797 | 3016 | 702 | 5 | 3.51 | 10.5862 | m2 | 3 | Alu. |  | 5 | 85.7479 | 1 | 1
55 | PR2306 (SO-777) | Chapel Street | Panel | Panel PG1-76 451x978 (Girth 612 x 1114) | CSS-P1-PG1 | PG1-76 | West | (L2-6) | Grey: 56B0/4850 | Outside | 451 | 978 | 5 | 4.89 | 2.2054 | 612 | 1114 | 5 | 5.57 | 3.4088 | m2 | 3 | Alu. |  | 5 | 27.6116 | 1 | 1
56 | PR2306 (SO-777) | Chapel Street | Stiffener | Stiffener PG1-76 50x978 (Girth 198 x 978) | CSS-P1-PG1 | PG1-76 | West | (L2-6) | Mill Finish | Outside | 50 | 978 | 5 | 4.89 | 0.2445 | 198 | 978 | 5 | 4.89 | 0.96822 | m2 | 3 | Alu. |  | 5 | 7.8426 | 1 | 1
57 | PR2306 (SO-777) | Chapel Street | Panel | Panel PG1-75 2855x566 (Girth 3016 x 702) | CSS-P2-PG1 | PG1-75 | West | (L7-10) | Grey: 56B0/4850 | Outside | 2855 | 566 | 4 | 2.264 | 6.4637 | 3016 | 702 | 4 | 2.808 | 8.4689 | m2 | 3 | Alu. |  | 4 | 68.5983 | 2 | 1
58 | PR2306 (SO-777) | Chapel Street | Panel | Panel PG1-76 451x978 (Girth 612 x 1114) | CSS-P2-PG1 | PG1-76 | West | (L7-10) | Grey: 56B0/4850 | Outside | 451 | 978 | 4 | 3.912 | 1.7643 | 612 | 1114 | 4 | 4.456 | 2.7271 | m2 | 3 | Alu. |  | 4 | 22.0893 | 2 | 1
59 | PR2306 (SO-777) | Chapel Street | Stiffener | Stiffener PG1-76 50x978 (Girth 198 x 978) | CSS-P2-PG1 | PG1-76 | West | (L7-10) | Mill Finish | Outside | 50 | 978 | 4 | 3.912 | 0.1956 | 198 | 978 | 4 | 3.912 | 0.77458 | m2 | 3 | Alu. |  | 4 | 6.2741 | 2 | 1
60 | PR2306 (SO-777) | Chapel Street | Panel | Panel PG1-75 2855x566 (Girth 3016 x 702) | CSS-P3-PG1 | PG1-75 | West | (L11-16) | Grey: 56B0/4850 | Outside | 2855 | 566 | 2 | 1.132 | 3.2319 | 3016 | 702 | 2 | 1.404 | 4.2345 | m2 | 3 | Alu. |  | 2 | 34.2992 | 3 | 1
61 | PR2306 (SO-777) | Chapel Street | Panel | Panel PG1-76 451x978 (Girth 612 x 1114) | CSS-P3-PG1 | PG1-76 | West | (L11-16) | Grey: 56B0/4850 | Outside | 451 | 978 | 3 | 2.934 | 1.3232 | 612 | 1114 | 3 | 3.342 | 2.0453 | m2 | 3 | Alu. |  | 3 | 16.567 | 3 | 1
62 | PR2306 (SO-777) | Chapel Street | Stiffener | Stiffener PG1-76 50x978 (Girth 198 x 978) | CSS-P3-PG1 | PG1-76 | West | (L11-16) | Mill Finish | Outside | 50 | 978 | 3 | 2.934 | 0.1467 | 198 | 978 | 3 | 2.934 | 0.58093 | m2 | 3 | Alu. |  | 3 | 4.7055 | 3 | 1
63 | PR2306 (SO-777) | Chapel Street | Panel | Panel PG1-77 465x978 (Girth 626 x 1114) | CSS-P3-PG1 | PG1-77 | West | (L11-16) | Grey: 56B0/4850 | Outside | 465 | 978 | 1 | 0.978 | 0.45477 | 626 | 1114 | 1 | 1.114 | 0.69736 | m2 | 3 | Alu. |  | 1 | 5.6486 | 3 | 1
64 | PR2306 (SO-777) | Chapel Street | Stiffener | Stiffener PG1-77 50x978 (Girth 198 x 978) | CSS-P3-PG1 | PG1-77 | West | (L11-16) | Mill Finish | Outside | 50 | 978 | 1 | 0.978 | 0.0489 | 198 | 978 | 1 | 0.978 | 0.19364 | m2 | 3 | Alu. |  | 1 | 1.5685 | 3 | 1
65 | PR2306 (SO-777) | Chapel Street | Pressing (LH Jamb) | Pressing (LH Jamb) PS01-A 45x2413 (Girth 596 x 2413) | CSS-P1-PS01 | PS01-A | South | (L2-6) | Bronze: 56PRR/4163 | Outside | 45 | 2413 | 10 | 24.13 | 1.0858 | 596 | 2413 | 10 | 24.13 | 14.3815 | m2 | 3 | Alu. |  | 45 | 116.49 | 1 | 1
66 | PR2306 (SO-777) | Chapel Street | End Cap | End Cap PS01-A 45x147 (Girth 45 x 147) | CSS-P1-PS01 | PS01-A | South | (L2-6) | Bronze: 56PRR/4163 | Outside | 45 | 147 | 10 | 1.47 | 0.06615 | 45 | 147 | 10 | 1.47 | 0.06615 | m2 | 3 | Alu. | 3.39 | 45 | 0.53582 | 1 | 1
67 | PR2306 (SO-777) | Chapel Street | Angle 25x50 | Angle 25x50 PS01-A 50x50 (Girth 75 x 50) | CSS-P1-PS01 | PS01-A | South | (L2-6) | Mill Finish | NA | 50 | 50 | 10 | 0.5 | 0.025 | 75 | 50 | 10 | 0.5 | 0.0375 | m2 | 3 | Alu. |  | 45 | 0.30375 | 1 | 1
68 | PR2306 (SO-777) | Chapel Street | Pressing (LH Jamb) | Pressing (LH Jamb) PS01-A 45x2413 (Girth 596 x 2413) | CSS-P2-PS01 | PS01-A | South | (L7-10) | Bronze: 56PRR/4163 | Outside | 45 | 2413 | 8 | 19.304 | 0.86868 | 596 | 2413 | 8 | 19.304 | 11.5052 | m2 | 3 | Alu. |  | 36 | 93.192 | 2 | 1
69 | PR2306 (SO-777) | Chapel Street | End Cap | End Cap PS01-A 45x147 (Girth 45 x 147) | CSS-P2-PS01 | PS01-A | South | (L7-10) | Bronze: 56PRR/4163 | Outside | 45 | 147 | 8 | 1.176 | 0.05292 | 45 | 147 | 8 | 1.176 | 0.05292 | m2 | 3 | Alu. | 2.712 | 36 | 0.42865 | 2 | 1
70 | PR2306 (SO-777) | Chapel Street | Angle 25x50 | Angle 25x50 PS01-A 50x50 (Girth 75 x 50) | CSS-P2-PS01 | PS01-A | South | (L7-10) | Mill Finish | NA | 50 | 50 | 8 | 0.4 | 0.02 | 75 | 50 | 8 | 0.4 | 0.03 | m2 | 3 | Alu. |  | 36 | 0.243 | 2 | 1
71 | PR2306 (SO-777) | Chapel Street | Pressing (LH Jamb) | Pressing (LH Jamb) PS01-A 45x2413 (Girth 596 x 2413) | CSS-P3-PS01 | PS01-A | South | (L11-16) | Bronze: 56PRR/4163 | Outside | 45 | 2413 | 4 | 9.652 | 0.43434 | 596 | 2413 | 4 | 9.652 | 5.7526 | m2 | 3 | Alu. |  | 36 | 46.596 | 3 | 1
72 | PR2306 (SO-777) | Chapel Street | End Cap | End Cap PS01-A 45x147 (Girth 45 x 147) | CSS-P3-PS01 | PS01-A | South | (L11-16) | Bronze: 56PRR/4163 | Outside | 45 | 147 | 4 | 0.588 | 0.02646 | 45 | 147 | 4 | 0.588 | 0.02646 | m2 | 3 | Alu. | 1.356 | 36 | 0.21433 | 3 | 1
73 | PR2306 (SO-777) | Chapel Street | Angle 25x50 | Angle 25x50 PS01-A 50x50 (Girth 75 x 50) | CSS-P3-PS01 | PS01-A | South | (L11-16) | Mill Finish | NA | 50 | 50 | 4 | 0.2 | 0.01 | 75 | 50 | 4 | 0.2 | 0.015 | m2 | 3 | Alu. |  | 36 | 0.1215 | 3 | 1
74 | PR2306 (SO-777) | Chapel Street | Pressing (RH Jamb) | Pressing (RH Jamb) PS02-A 45x2413 (Girth 602 x 2413) | CSS-P1-PS02 | PS02-A | South | (L2-6) | Bronze: 56PRR/4163 | Outside | 45 | 2413 | 10 | 24.13 | 1.0858 | 602 | 2413 | 10 | 24.13 | 14.5263 | m2 | 3 | Alu. |  | 45 | 117.6627 | 1 | 1
75 | PR2306 (SO-777) | Chapel Street | End Cap | End Cap PS02-A 45x150 (Girth 45 x 150) | CSS-P1-PS02 | PS02-A | South | (L2-6) | Bronze: 56PRR/4163 | Outside | 45 | 150 | 10 | 1.5 | 0.0675 | 45 | 150 | 10 | 1.5 | 0.0675 | m2 | 3 | Alu. | 3.45 | 45 | 0.54675 | 1 | 1
76 | PR2306 (SO-777) | Chapel Street | Angle 25x50 | Angle 25x50 PS02-A 50x50 (Girth 75 x 50) | CSS-P1-PS02 | PS02-A | South | (L2-6) | Mill Finish | NA | 50 | 50 | 10 | 0.5 | 0.025 | 75 | 50 | 10 | 0.5 | 0.0375 | m2 | 3 | Alu. |  | 45 | 0.30375 | 1 | 1
77 | PR2306 (SO-777) | Chapel Street | Pressing (RH Jamb) | Pressing (RH Jamb) PS02-A 45x2413 (Girth 602 x 2413) | CSS-P2-PS02 | PS02-A | South | (L7-10) | Bronze: 56PRR/4163 | Outside | 45 | 2413 | 8 | 19.304 | 0.86868 | 602 | 2413 | 8 | 19.304 | 11.621 | m2 | 3 | Alu. |  | 36 | 94.1302 | 2 | 1
78 | PR2306 (SO-777) | Chapel Street | End Cap | End Cap PS02-A 45x150 (Girth 45 x 150) | CSS-P2-PS02 | PS02-A | South | (L7-10) | Bronze: 56PRR/4163 | Outside | 45 | 150 | 8 | 1.2 | 0.054 | 45 | 150 | 8 | 1.2 | 0.054 | m2 | 3 | Alu. | 2.76 | 36 | 0.4374 | 2 | 1
79 | PR2306 (SO-777) | Chapel Street | Angle 25x50 | Angle 25x50 PS02-A 50x50 (Girth 75 x 50) | CSS-P2-PS02 | PS02-A | South | (L7-10) | Mill Finish | NA | 50 | 50 | 8 | 0.4 | 0.02 | 75 | 50 | 8 | 0.4 | 0.03 | m2 | 3 | Alu. |  | 36 | 0.243 | 2 | 1
80 | PR2306 (SO-777) | Chapel Street | Pressing (RH Jamb) | Pressing (RH Jamb) PS02-A 45x2413 (Girth 602 x 2413) | CSS-P3-PS02 | PS02-A | South | (L11-16) | Bronze: 56PRR/4163 | Outside | 45 | 2413 | 4 | 9.652 | 0.43434 | 602 | 2413 | 4 | 9.652 | 5.8105 | m2 | 3 | Alu. |  | 35 | 47.0651 | 3 | 1
81 | PR2306 (SO-777) | Chapel Street | End Cap | End Cap PS02-A 45x150 (Girth 45 x 150) | CSS-P3-PS02 | PS02-A | South | (L11-16) | Bronze: 56PRR/4163 | Outside | 45 | 150 | 4 | 0.6 | 0.027 | 45 | 150 | 4 | 0.6 | 0.027 | m2 | 3 | Alu. | 1.38 | 35 | 0.2187 | 3 | 1
82 | PR2306 (SO-777) | Chapel Street | Angle 25x50 | Angle 25x50 PS02-A 50x50 (Girth 75 x 50) | CSS-P3-PS02 | PS02-A | South | (L11-16) | Mill Finish | NA | 50 | 50 | 4 | 0.2 | 0.01 | 75 | 50 | 4 | 0.2 | 0.015 | m2 | 3 | Alu. |  | 35 | 0.1215 | 3 | 1
83 | PR2306 (SO-777) | Chapel Street | Pressing (Cill) | Pressing (Cill) PS03-A 45x1015 (Girth 563 x 1015) | CSS-P1-PS03 | PS03-A | South | (L2-6) | Bronze: 56PRR/4163 | Outside | 45 | 1015 | 10 | 10.15 | 0.45675 | 563 | 1015 | 10 | 10.15 | 5.7145 | m2 | 3 | Alu. |  | 45 | 46.287 | 1 | 1
84 | PR2306 (SO-777) | Chapel Street | Pressing (Cill) | Pressing (Cill) PS03-A 45x1015 (Girth 563 x 1015) | CSS-P2-PS03 | PS03-A | South | (L7-10) | Bronze: 56PRR/4163 | Outside | 45 | 1015 | 8 | 8.12 | 0.3654 | 563 | 1015 | 8 | 8.12 | 4.5716 | m2 | 3 | Alu. |  | 36 | 37.0296 | 2 | 1
85 | PR2306 (SO-777) | Chapel Street | Pressing (Cill) | Pressing (Cill) PS03-A 45x1015 (Girth 563 x 1015) | CSS-P3-PS03 | PS03-A | South | (L11-16) | Bronze: 56PRR/4163 | Outside | 45 | 1015 | 4 | 4.06 | 0.1827 | 563 | 1015 | 4 | 4.06 | 2.2858 | m2 | 3 | Alu. |  | 35 | 18.5148 | 3 | 1
86 | PR2306 (SO-777) | Chapel Street | Pressing (Head) | Pressing (Head) PS04-A 45x1105 (Girth 630 x 1105) | CSS-P1-PS04 | PS04-A | South | (L2-6) | Bronze: 56PRR/4163 | Outside | 45 | 1105 | 10 | 11.05 | 0.49725 | 630 | 1105 | 10 | 11.05 | 6.9615 | m2 | 3 | Alu. |  | 45 | 56.3882 | 1 | 1
87 | PR2306 (SO-777) | Chapel Street | End Cap | End Cap PS04-A 45x150 (Girth 45 x 150) | CSS-P1-PS04 | PS04-A | South | (L2-6) | Bronze: 56PRR/4163 | Outside | 45 | 150 | 20 | 3 | 0.135 | 45 | 150 | 20 | 3 | 0.135 | m2 | 3 | Alu. | 6.9 | 90 | 1.0935 | 1 | 1
88 | PR2306 (SO-777) | Chapel Street | Pressing (Head) | Pressing (Head) PS04-A 45x1105 (Girth 630 x 1105) | CSS-P2-PS04 | PS04-A | South | (L7-10) | Bronze: 56PRR/4163 | Outside | 45 | 1105 | 8 | 8.84 | 0.3978 | 630 | 1105 | 8 | 8.84 | 5.5692 | m2 | 3 | Alu. |  | 36 | 45.1105 | 2 | 1
89 | PR2306 (SO-777) | Chapel Street | End Cap | End Cap PS04-A 45x150 (Girth 45 x 150) | CSS-P2-PS04 | PS04-A | South | (L7-10) | Bronze: 56PRR/4163 | Outside | 45 | 150 | 16 | 2.4 | 0.108 | 45 | 150 | 16 | 2.4 | 0.108 | m2 | 3 | Alu. | 5.52 | 72 | 0.8748 | 2 | 1
90 | PR2306 (SO-777) | Chapel Street | Pressing (Head) | Pressing (Head) PS04-A 45x1105 (Girth 630 x 1105) | CSS-P3-PS04 | PS04-A | South | (L7-10) | Bronze: 56PRR/4163 | Outside | 45 | 1105 | 4 | 4.42 | 0.1989 | 630 | 1105 | 4 | 4.42 | 2.7846 | m2 | 3 | Alu. |  | 35 | 22.5553 | 3 | 1
91 | PR2306 (SO-777) | Chapel Street | End Cap | End Cap PS04-A 45x150 (Girth 45 x 150) | CSS-P3-PS04 | PS04-A | South | (L7-10) | Bronze: 56PRR/4163 | Outside | 45 | 150 | 8 | 1.2 | 0.054 | 45 | 150 | 8 | 1.2 | 0.054 | m2 | 3 | Alu. | 2.76 | 70 | 0.4374 | 3 | 1
92 | PR2306 (SO-777) | Chapel Street | Angle 25x25 | Angle 25x25 PS13-A-1 25x2368 (Girth 50 x 2368) | CSS-P1-PS13 | PS13-A-1 | South | (L2-6) | Bronze: 56PRR/4163 | Outside | 25 | 2368 | 44 | 104.192 | 2.6048 | 50 | 2368 | 44 | 104.192 | 5.2096 | m2 | 1.5 | Alu. |  | 90 | 21.0989 | 1 | 1
93 | PR2306 (SO-777) | Chapel Street | Angle 25x25 | Angle 25x25 PS13-A-2 25x1074 (Girth 50 x 1074) | CSS-P1-PS13 | PS13-A-2 | South | (L2-6) | Bronze: 56PRR/4163 | Outside | 25 | 1074 | 22 | 23.628 | 0.5907 | 50 | 1074 | 22 | 23.628 | 1.1814 | m2 | 1.5 | Alu. |  | 45 | 4.7847 | 1 | 1
94 | PR2306 (SO-777) | Chapel Street | Angle 30x30 | Angle 30x30 PS14-A-1 30x1013 (Girth 60 x 1013) | CSS-P1-PS14 | PS14-A-1 | South | (L2-6) | Bronze: 56PRR/4163 | Outside | 30 | 1013 | 22 | 22.286 | 0.66858 | 60 | 1013 | 22 | 22.286 | 1.3372 | m2 | 2 | Alu. |  | 45 | 7.2207 | 1 | 1
95 | PR2306 (SO-777) | Chapel Street | Angle 25x25 | Angle 25x25 PS13-I-1 25x2328 (Girth 50 x 2328) | CSS-P1-PS15 | PS15-I.1-1 | West | (L2-6) | Grey: 56B0/4850 | Outside | 25 | 2373 | 10 | 23.73 | 0.59325 | 50 | 2328 | 10 | 23.28 | 1.164 | m2 | 1.5 | Alu. |  | 10 | 4.7142 | 1 | 1
96 | PR2306 (SO-777) | Chapel Street | Angle 25x25 | Angle 25x25 PS13-I-2 25x972 (Girth 50 x 972) | CSS-P1-PS15 | PS15-I.1-2 | West | (L2-6) | Grey: 56B0/4850 | Outside | 25 | 978 | 5 | 4.89 | 0.12225 | 50 | 972 | 5 | 4.86 | 0.243 | m2 | 1.5 | Alu. |  | 5 | 0.98415 | 1 | 1
97 | PR2306 (SO-777) | Chapel Street | Angle 25x25 | Angle 25x25 PS13-I-1 25x2328 (Girth 50 x 2328) | CSS-P2-PS15 | PS15-I.1-1 | West | (L7-10) | Grey: 56B0/4850 | Outside | 25 | 2373 | 8 | 18.984 | 0.4746 | 50 | 2328 | 8 | 18.624 | 0.9312 | m2 | 1.5 | Alu. |  | 8 | 3.7714 | 2 | 1
98 | PR2306 (SO-777) | Chapel Street | Angle 25x25 | Angle 25x25 PS13-I-2 25x972 (Girth 50 x 972) | CSS-P2-PS15 | PS15-I.1-2 | West | (L7-10) | Grey: 56B0/4850 | Outside | 25 | 978 | 4 | 3.912 | 0.0978 | 50 | 972 | 4 | 3.888 | 0.1944 | m2 | 1.5 | Alu. |  | 4 | 0.78732 | 2 | 1
99 | PR2306 (SO-777) | Chapel Street | Angle 25x25 | Angle 25x25 PS13-I-1 25x2328 (Girth 50 x 2328) | CSS-P3-PS15 | PS15-I.1-1 | West | (L11-16) | Grey: 56B0/4850 | Outside | 25 | 2373 | 6 | 14.238 | 0.35595 | 50 | 2328 | 6 | 13.968 | 0.6984 | m2 | 1.5 | Alu. |  | 6 | 2.8285 | 3 | 1
100 | PR2306 (SO-777) | Chapel Street | Angle 25x25 | Angle 25x25 PS13-I-2 25x972 (Girth 50 x 972) | CSS-P3-PS15 | PS15-I.1-2 | West | (L11-16) | Grey: 56B0/4850 | Outside | 25 | 978 | 3 | 2.934 | 0.07335 | 50 | 972 | 3 | 2.916 | 0.1458 | m2 | 1.5 | Alu. |  | 3 | 0.59049 | 3 | 1
101 | PR2306 (SO-777) | Chapel Street | Angle 30x30 | Angle 30x30 PS15-I.1-2 30x954 (Girth 60 x 954) | CSS-P1-PS16 | PS15-I.1-2 | West | (L2-6) | Grey: 56B0/4850 | Outside | 30 | 954 | 5 | 4.77 | 0.1431 | 60 | 954 | 5 | 4.77 | 0.2862 | m2 | 3 | Alu. |  | 5 | 2.3182 | 1 | 1
102 | PR2306 (SO-777) | Chapel Street | Angle 30x30 | Angle 30x30 PS15-I.1-2 30x954 (Girth 60 x 954) | CSS-P2-PS16 | PS15-I.1-2 | West | (L7-10) | Grey: 56B0/4850 | Outside | 30 | 954 | 4 | 3.816 | 0.11448 | 60 | 954 | 4 | 3.816 | 0.22896 | m2 | 3 | Alu. |  | 4 | 1.8546 | 2 | 1
103 | PR2306 (SO-777) | Chapel Street | Angle 30x30 | Angle 30x30 PS15-I.1-2 30x954 (Girth 60 x 954) | CSS-P3-PS16 | PS15-I.1-2 | West | (L11-16) | Grey: 56B0/4850 | Outside | 30 | 954 | 3 | 2.862 | 85860 | 60 | 954 | 3 | 2.862 | 0.17172 | m2 | 3 | Alu. |  | 3 | 1.3909 | 3 | 1
[13 empty] | 938 | 944.119 | 86275.5555 |  |  | 938 | 973.199 | 658.3284 |  |  |  |  | 2036 | 5289.2897

## Fab. Shedule
Ref. | Project/SO | Project Name | Description | DWG | Level | Elev. | Prod. | Qty | Colour | PPC Side | Bend | Weight KG | Total Weight | Height | Width | Qty | Total M2 | Height | Width | Qty | Total M2 | Unit | Thickness | Material | Comments
1 | PR2306 (SO-777) | Chapel Street | Panel PB1-01 470x1105 (Girth 631 x 1241) | CSS-P1-PB1 | PB1-01 | South | (L2-6) | 2 | Bronze: 56PRR/4163 | Outside | Y | 6.3429 | 12.6858 | 470 | 1105 | 2 | 1.0387 | 631 | 1241 | 2 | 1.5661 | m2 | 3 | 0 | 9
2 | PR2306 (SO-777) | Chapel Street | Stiffener PB1-01 50x1105 (Girth 198 x 1105) | CSS-P1-PB1 | PB1-01 | South | (L2-6) | 2 | Mill Finish | Outside | Y | 1.7722 | 3.5444 | 50 | 1105 | 2 | 0.1105 | 198 | 1105 | 2 | 0.43758 | m2 | 3 | 0 | 9
3 | PR2306 (SO-777) | Chapel Street | Panel PB1-02 470x907 (Girth 631 x 1043) | CSS-P1-PB1 | PB1-02 | South | (L2-6) | 2 | Bronze: 56PRR/4163 | Outside | Y | 5.3309 | 10.6618 | 470 | 907 | 2 | 0.85258 | 631 | 1043 | 2 | 1.3163 | m2 | 3 | 0 | 2
4 | PR2306 (SO-777) | Chapel Street | Stiffener PB1-02 50x907 (Girth 198 x 907) | CSS-P1-PB1 | PB1-02 | South | (L2-6) | 2 | Mill Finish | Outside | Y | 1.4546 | 2.9093 | 50 | 907 | 2 | 0.0907 | 198 | 907 | 2 | 0.35917 | m2 | 3 | 0 | 2
5 | PR2306 (SO-777) | Chapel Street | Panel PB1-03 470x280 (Girth 631 x 416) | CSS-P1-PB1 | PB1-03 | South | (L2-6) | 2 | Bronze: 56PRR/4163 | Outside | Y | 2.1262 | 4.2524 | 470 | 280 | 2 | 0.2632 | 631 | 416 | 2 | 0.52499 | m2 | 3 | 0 | 6
6 | PR2306 (SO-777) | Chapel Street | Panel PB1-07 2855x907 (Girth 3016 x 1043) | CSS-P1-PB1 | PB1-07 | South | (L2-6) | 10 | Bronze: 56PRR/4163 | Outside | Y | 25.4801 | 254.8007 | 2855 | 907 | 10 | 25.8949 | 3016 | 1043 | 10 | 31.4569 | m2 | 3 | 0 | 10
7 | PR2306 (SO-777) | Chapel Street | Stiffener PB1-07 50x907 (Girth 198 x 907) | CSS-P1-PB1 | PB1-07 | South | (L2-6) | 40 | Mill Finish | Outside | Y | 1.4546 | 58.1859 | 50 | 907 | 40 | 1.814 | 198 | 907 | 40 | 7.1834 | m2 | 3 | 0 | 40
8 | PR2306 (SO-777) | Chapel Street | Panel PB1-03 470x280 (Girth 631 x 416) | CSS-P1-PB1 | PB1-03 | West | (L2-6) | 3 | Bronze: 56PRR/4163 | Outside | Y | 2.1262 | 6.3787 | 470 | 280 | 3 | 0.3948 | 631 | 416 | 3 | 0.78749 | m2 | 3 | 0 | 3
9 | PR2306 (SO-777) | Chapel Street | Panel PB1-30 470x1011 (Girth 631 x 1147) | CSS-P1-PB1 | PB1-30 | West | (L2-6) | 5 | Bronze: 56PRR/4163 | Outside | Y | 5.8624 | 29.3122 | 470 | 1011 | 5 | 2.3758 | 631 | 1147 | 5 | 3.6188 | m2 | 3 | 0 | 5
10 | PR2306 (SO-777) | Chapel Street | Stiffener PB1-30 50x1011 (Girth 198 x 1011) | CSS-P1-PB1 | PB1-30 | West | (L2-6) | 5 | Mill Finish | Outside | Y | 1.6214 | 8.1072 | 50 | 1011 | 5 | 0.25275 | 198 | 1011 | 5 | 1.0009 | m2 | 3 | 0 | 5
11 | PR2306 (SO-777) | Chapel Street | Panel PB1-33 470x639 (Girth 631 x 775) | CSS-P1-PB1 | PB1-33 | West | (L2-6) | 1 | Bronze: 56PRR/4163 | Outside | Y | 3.9611 | 3.9611 | 470 | 639 | 1 | 0.30033 | 631 | 775 | 1 | 0.48902 | m2 | 3 | 0 | 1
12 | PR2306 (SO-777) | Chapel Street | Panel PB1-08 2855x280 (Girth 3016 x 416) | CSS-P1-PB1 | PB1-08 | West | (L2-6) | 15 | Bronze: 56PRR/4163 | Outside | Y | 10.1627 | 152.4407 | 2855 | 280 | 15 | 11.991 | 3016 | 416 | 15 | 18.8198 | m2 | 3 | 0 | 15
13 | PR2306 (SO-777) | Chapel Street | Panel PB1-31 2855x1011 (Girth 3016 x 1147) | CSS-P1-PB1 | PB1-31 | West | (L2-6) | 25 | Bronze: 56PRR/4163 | Outside | Y | 28.0208 | 700.5188 | 2855 | 1011 | 25 | 72.1601 | 3016 | 1147 | 25 | 86.4838 | m2 | 3 | 0 | 25
14 | PR2306 (SO-777) | Chapel Street | Stiffener PB1-31 50x1011 (Girth 198 x 1011) | CSS-P1-PB1 | PB1-31 | West | (L2-6) | 100 | Mill Finish | Outside | Y | 1.6214 | 162.1442 | 50 | 1011 | 100 | 5.055 | 198 | 1011 | 100 | 20.0178 | m2 | 3 | 0 | 100
15 | PR2306 (SO-777) | Chapel Street | Panel PB1-34 2855x639 (Girth 3016 x 775) | CSS-P1-PB1 | PB1-34 | West | (L2-6) | 5 | Bronze: 56PRR/4163 | Outside | Y | 18.9329 | 94.6647 | 2855 | 639 | 5 | 9.1217 | 3016 | 775 | 5 | 11.687 | m2 | 3 | 0 | 5
16 | PR2306 (SO-777) | Chapel Street | Panel PB1-07 2855x907 (Girth 3016 x 1043) | CSS-P2-PB1 | PB1-07 | South | (L7-10) | 8 | Bronze: 56PRR/4163 | Outside | Y | 25.4801 | 203.8406 | 2855 | 907 | 8 | 20.7159 | 3016 | 1043 | 8 | 25.1655 | m2 | 3 | 0 | 8
17 | PR2306 (SO-777) | Chapel Street | Stiffener PB1-07 50x907 (Girth 198 x 907) | CSS-P2-PB1 | PB1-07 | South | (L7-10) | 32 | Mill Finish | Outside | Y | 1.4546 | 46.5487 | 50 | 907 | 32 | 1.4512 | 198 | 907 | 32 | 5.7468 | m2 | 3 | 0 | 32
18 | PR2306 (SO-777) | Chapel Street | Panel PB1-08 2855x280 (Girth 3016 x 416) | CSS-P2-PB1 | PB1-08 | West | (L7-10) | 12 | Bronze: 56PRR/4163 | Outside | Y | 10.1627 | 121.9526 | 2855 | 280 | 12 | 9.5928 | 3016 | 416 | 12 | 15.0559 | m2 | 3 | 0 | 12
19 | PR2306 (SO-777) | Chapel Street | Panel PB1-31 2855x1011 (Girth 3016 x 1147) | CSS-P2-PB1 | PB1-31 | West | (L7-10) | 20 | Bronze: 56PRR/4163 | Outside | Y | 28.0208 | 560.415 | 2855 | 1011 | 20 | 57.7281 | 3016 | 1147 | 20 | 69.187 | m2 | 3 | 0 | 20
20 | PR2306 (SO-777) | Chapel Street | Stiffener PB1-31 50x1011 (Girth 198 x 1011) | CSS-P2-PB1 | PB1-31 | West | (L7-10) | 80 | Mill Finish | Outside | Y | 1.6214 | 129.7153 | 50 | 1011 | 80 | 4.044 | 198 | 1011 | 80 | 16.0142 | m2 | 3 | 0 | 80
21 | PR2306 (SO-777) | Chapel Street | Panel PB1-34 2855x639 (Girth 3016 x 775) | CSS-P2-PB1 | PB1-34 | West | (L7-10) | 4 | Bronze: 56PRR/4163 | Outside | Y | 18.9329 | 75.7318 | 2855 | 639 | 4 | 7.2974 | 3016 | 775 | 4 | 9.3496 | m2 | 3 | 0 | 4
22 | PR2306 (SO-777) | Chapel Street | Panel PB1-06 377x1105 (Girth 538 x 1241) | CSS-P3-PB1 | PB1-06 | South | (L11-16) | 22 | Bronze: 56PRR/4163 | Outside | Y | 5.408 | 118.9767 | 377 | 1105 | 22 | 9.1649 | 538 | 1241 | 22 | 14.6885 | m2 | 3 | 0 | 32
23 | PR2306 (SO-777) | Chapel Street | Stiffener PB1-06 50x1105 (Girth 198 x 1105) | CSS-P3-PB1 | PB1-06 | South | (L11-16) | 22 | Mill Finish | Outside | Y | 1.7722 | 38.9884 | 50 | 1105 | 22 | 1.2155 | 198 | 1105 | 22 | 4.8134 | m2 | 3 | 0 | 32
24 | PR2306 (SO-777) | Chapel Street | Panel PB1-07 2855x907 (Girth 3016 x 1043) | CSS-P3-PB1 | PB1-07 | South | (L11-16) | 4 | Bronze: 56PRR/4163 | Outside | Y | 25.4801 | 101.9203 | 2855 | 907 | 4 | 10.3579 | 3016 | 1043 | 4 | 12.5828 | m2 | 3 | 0 | 4
25 | PR2306 (SO-777) | Chapel Street | Stiffener PB1-07 50x907 (Girth 198 x 907) | CSS-P3-PB1 | PB1-07 | South | (L11-16) | 16 | Mill Finish | Outside | Y | 1.4546 | 23.2743 | 50 | 907 | 16 | 0.7256 | 198 | 907 | 16 | 2.8734 | m2 | 3 | 0 | 16
26 | PR2306 (SO-777) | Chapel Street | Panel PB1-08 2855x280 (Girth 3016 x 416) | CSS-P3-PB1 | PB1-08 | South | (L11-16) | 11 | Bronze: 56PRR/4163 | Outside | Y | 10.1627 | 111.7898 | 2855 | 280 | 11 | 8.7934 | 3016 | 416 | 11 | 13.8012 | m2 | 3 | 0 | 22
27 | PR2306 (SO-777) | Chapel Street | Panel PB1-11 465x1105 (Girth 626 x 1241) | CSS-P3-PB1 | PB1-11 | South | (L11-16) | 2 | Bronze: 56PRR/4163 | Outside | Y | 6.2926 | 12.5852 | 465 | 1105 | 2 | 1.0276 | 626 | 1241 | 2 | 1.5537 | m2 | 3 | 0 | 9
28 | PR2306 (SO-777) | Chapel Street | Stiffener PB1-11 50x1105 (Girth 198 x 1105) | CSS-P3-PB1 | PB1-11 | South | (L11-16) | 2 | Mill Finish | Outside | Y | 1.7722 | 3.5444 | 50 | 1105 | 2 | 0.1105 | 198 | 1105 | 2 | 0.43758 | m2 | 3 | 0 | 9
29 | PR2306 (SO-777) | Chapel Street | Panel PB1-12 465x907 (Girth 626 x 1043) | CSS-P3-PB1 | PB1-12 | South | (L11-16) | 2 | Bronze: 56PRR/4163 | Outside | Y | 5.2886 | 10.5773 | 465 | 907 | 2 | 0.84351 | 626 | 1043 | 2 | 1.3058 | m2 | 3 | 0 | 2
30 | PR2306 (SO-777) | Chapel Street | Stiffener PB1-12 50x907 (Girth 198 x 907) | CSS-P3-PB1 | PB1-12 | South | (L11-16) | 2 | Mill Finish | Outside | Y | 1.4546 | 2.9093 | 50 | 907 | 2 | 0.0907 | 198 | 907 | 2 | 0.35917 | m2 | 3 | 0 | 2
31 | PR2306 (SO-777) | Chapel Street | Panel PB1-13 465x280 (Girth 626 x 416) | CSS-P3-PB1 | PB1-13 | South | (L11-16) | 1 | Bronze: 56PRR/4163 | Outside | Y | 2.1094 | 2.1094 | 465 | 280 | 1 | 0.1302 | 626 | 416 | 1 | 0.26042 | m2 | 3 | 0 | 6
32 | PR2306 (SO-777) | Chapel Street | Panel PB1-08 2855x280 (Girth 3016 x 416) | CSS-P3-PB1 | PB1-08 | West | (L11-16) | 6 | Bronze: 56PRR/4163 | Outside | Y | 10.1627 | 60.9763 | 2855 | 280 | 6 | 4.7964 | 3016 | 416 | 6 | 7.5279 | m2 | 3 | 0 | 6
33 | PR2306 (SO-777) | Chapel Street | Panel PB1-31 2855x1011 (Girth 3016 x 1147) | CSS-P3-PB1 | PB1-31 | West | (L11-16) | 10 | Bronze: 56PRR/4163 | Outside | Y | 28.0208 | 280.2075 | 2855 | 1011 | 10 | 28.864 | 3016 | 1147 | 10 | 34.5935 | m2 | 3 | 0 | 10
34 | PR2306 (SO-777) | Chapel Street | Stiffener PB1-31 50x1011 (Girth 198 x 1011) | CSS-P3-PB1 | PB1-31 | West | (L11-16) | 40 | Mill Finish | Outside | Y | 1.6214 | 64.8577 | 50 | 1011 | 40 | 2.022 | 198 | 1011 | 40 | 8.0071 | m2 | 3 | 0 | 40
35 | PR2306 (SO-777) | Chapel Street | Panel PB1-34 2855x639 (Girth 3016 x 775) | CSS-P3-PB1 | PB1-34 | West | (L11-16) | 2 | Bronze: 56PRR/4163 | Outside | Y | 18.9329 | 37.8659 | 2855 | 639 | 2 | 3.6487 | 3016 | 775 | 2 | 4.6748 | m2 | 3 | 0 | 2
36 | PR2306 (SO-777) | Chapel Street | Panel PB1-32 465x1011 (Girth 626 x 1147) | CSS-P3-PB1 | PB1-32 | West | (L11-16) | 5 | Bronze: 56PRR/4163 | Outside | Y | 5.816 | 29.0799 | 465 | 1011 | 5 | 2.3506 | 626 | 1147 | 5 | 3.5901 | m2 | 3 | 0 | 5
37 | PR2306 (SO-777) | Chapel Street | Stiffener PB1-32 50x1011 (Girth 198 x 1011) | CSS-P3-PB1 | PB1-32 | West | (L11-16) | 5 | Mill Finish | Outside | Y | 1.6214 | 8.1072 | 50 | 1011 | 5 | 0.25275 | 198 | 1011 | 5 | 1.0009 | m2 | 3 | 0 | 5
38 | PR2306 (SO-777) | Chapel Street | Panel PB1-13 465x280 (Girth 626 x 416) | CSS-P3-PB1 | PB1-13 | West | (L11-16) | 2 | Bronze: 56PRR/4163 | Outside | Y | 2.1094 | 4.2187 | 465 | 280 | 2 | 0.2604 | 626 | 416 | 2 | 0.52083 | m2 | 3 | 0 | 2
39 | PR2306 (SO-777) | Chapel Street | Panel PB1-35 465x639 (Girth 626 x 775) | CSS-P3-PB1 | PB1-35 | West | (L11-16) | 1 | Bronze: 56PRR/4163 | Outside | Y | 3.9297 | 3.9297 | 465 | 639 | 1 | 0.29713 | 626 | 775 | 1 | 0.48515 | m2 | 3 | 0 | 5
40 | PR2306 (SO-777) | Chapel Street | Panel PB2-01 470x915 (Girth 631 x 985) | CSS-P1-PB2 | PB2-01 | South | (L2-6) | 1 | Bronze: 56PRR/4163 | Outside | Y | 5.0344 | 5.0344 | 470 | 915 | 1 | 0.43005 | 631 | 985 | 1 | 0.62153 | m2 | 3 | 0 | 1
41 | PR2306 (SO-777) | Chapel Street | Panel PB2-04 2855x915 (Girth 3016 x 985) | CSS-P1-PB2 | PB2-04 | South | (L2-6) | 5 | Bronze: 56PRR/4163 | Outside | Y | 24.0632 | 120.3158 | 2855 | 915 | 5 | 13.0616 | 3016 | 985 | 5 | 14.8538 | m2 | 3 | 0 | 5
42 | PR2306 (SO-777) | Chapel Street | Panel PB2-04 2855x915 (Girth 3016 x 985) | CSS-P2-PB2 | PB2-04 | South | (L7-10) | 4 | Bronze: 56PRR/4163 | Outside | Y | 24.0632 | 96.2526 | 2855 | 915 | 4 | 10.4493 | 3016 | 985 | 4 | 11.883 | m2 | 3 | 0 | 4
43 | PR2306 (SO-777) | Chapel Street | Panel PB2-04 2855x915 (Girth 3016 x 985) | CSS-P1-PB2 | PB2-04 | South | (L11-16) | 2 | Bronze: 56PRR/4163 | Outside | Y | 24.0632 | 48.1263 | 2855 | 915 | 2 | 5.2246 | 3016 | 985 | 2 | 5.9415 | m2 | 3 | 0 | 2
44 | PR2306 (SO-777) | Chapel Street | Panel PB2-07 2880x909 (Girth 3041 x 979) | CSS-P1-PB2 | PB2-07 | South | (L11-16) | 1 | Bronze: 56PRR/4163 | Outside | Y | 24.1148 | 24.1148 | 2880 | 909 | 1 | 2.6179 | 3041 | 979 | 1 | 2.9771 | m2 | 3 | 0 | 1
45 | PR2306 (SO-777) | Chapel Street | Panel PB3-04 2855x1177 (Girth 3016 x 1243) | CSS-P1-PB3 | PB3-04 | South | (L2-6) | 5 | Bronze: 56PRR/4163 | Outside | Y | 30.366 | 151.83 | 2855 | 1177 | 5 | 16.8017 | 3016 | 1243 | 5 | 18.7444 | m2 | 3 | 0 | 5
46 | PR2306 (SO-777) | Chapel Street | Panel PB3-04 2855x1177 (Girth 3016 x 1243) | CSS-P2-PB3 | PB3-04 | South | (L7-10) | 4 | Bronze: 56PRR/4163 | Outside | Y | 30.366 | 121.464 | 2855 | 1177 | 4 | 13.4413 | 3016 | 1243 | 4 | 14.9956 | m2 | 3 | 0 | 4
47 | PR2306 (SO-777) | Chapel Street | Panel PB3-07 465x621 (Girth 626 x 687) | CSS-P2-PB3 | PB3-07 | South | (L7-10) | 1 | Bronze: 56PRR/4163 | Outside | Y | 3.4835 | 3.4835 | 465 | 621 | 1 | 0.28876 | 626 | 687 | 1 | 0.43006 | m2 | 3 | 0 | 1
48 | PR2306 (SO-777) | Chapel Street | Panel PB3-04 2855x1177 (Girth 3016 x 1243) | CSS-P3-PB3 | PB3-04 | South | (L11-16) | 2 | Bronze: 56PRR/4163 | Outside | Y | 30.366 | 60.732 | 2855 | 1177 | 2 | 6.7207 | 3016 | 1243 | 2 | 7.4978 | m2 | 3 | 0 | 2
49 | PR2306 (SO-777) | Chapel Street | Corner Panel 1/2 PG&B-CNR4-2 465x190 (Girth 626 x 309) | CSS-P3-PG&B-CNR4 | PG&B-CNR4-2 | North | (L11-16) | 1 | Bronze: 56PRR/4163 | Outside | Y | 1.5668 | 1.5668 | 465 | 190 | 1 | 0.08835 | 626 | 309 | 1 | 0.19343 | m2 | 3 | 0 | 1
50 | PR2306 (SO-777) | Chapel Street | Corner Panel 2/2 PG&B-CNR4-2 465x310 (Girth 626 x 433) | CSS-P3-PG&B-CNR4 | PG&B-CNR4-2 | North | (L11-16) | 1 | Grey: 56B0/4850 | Outside | Y | 2.1956 | 2.1956 | 465 | 310 | 1 | 0.14415 | 626 | 433 | 1 | 0.27106 | m2 | 3 | 0 | 1
51 | PR2306 (SO-777) | Chapel Street | Panel PG1-73 755x978 (Girth 916 x 1114) | CSS-P1-PG1 | PG1-73 | West | (L2-6) | 1 | Grey: 56B0/4850 | Outside | Y | 8.2654 | 8.2654 | 755 | 978 | 1 | 0.73839 | 916 | 1114 | 1 | 1.0204 | m2 | 3 | 0 | 1
52 | PR2306 (SO-777) | Chapel Street | Stiffener PG1-73 50x978 (Girth 198 x 978) | CSS-P1-PG1 | PG1-73 | West | (L2-6) | 1 | Mill Finish | Outside | Y | 1.5685 | 1.5685 | 50 | 978 | 1 | 0.0489 | 198 | 978 | 1 | 0.19364 | m2 | 3 | 0 | 1
53 | PR2306 (SO-777) | Chapel Street | Panel PG1-74 755x566 (Girth 916 x 702) | CSS-P1-PG1 | PG1-74 | West | (L2-6) | 1 | Grey: 56B0/4850 | Outside | Y | 5.2086 | 5.2086 | 755 | 566 | 1 | 0.42733 | 916 | 702 | 1 | 0.64303 | m2 | 3 | 0 | 1
54 | PR2306 (SO-777) | Chapel Street | Panel PG1-75 2855x566 (Girth 3016 x 702) | CSS-P1-PG1 | PG1-75 | West | (L2-6) | 5 | Grey: 56B0/4850 | Outside | Y | 17.1496 | 85.7479 | 2855 | 566 | 5 | 8.0797 | 3016 | 702 | 5 | 10.5862 | m2 | 3 | 0 | 5
55 | PR2306 (SO-777) | Chapel Street | Panel PG1-76 451x978 (Girth 612 x 1114) | CSS-P1-PG1 | PG1-76 | West | (L2-6) | 5 | Grey: 56B0/4850 | Outside | Y | 5.5223 | 27.6116 | 451 | 978 | 5 | 2.2054 | 612 | 1114 | 5 | 3.4088 | m2 | 3 | 0 | 5
56 | PR2306 (SO-777) | Chapel Street | Stiffener PG1-76 50x978 (Girth 198 x 978) | CSS-P1-PG1 | PG1-76 | West | (L2-6) | 5 | Mill Finish | Outside | Y | 1.5685 | 7.8426 | 50 | 978 | 5 | 0.2445 | 198 | 978 | 5 | 0.96822 | m2 | 3 | 0 | 5
57 | PR2306 (SO-777) | Chapel Street | Panel PG1-75 2855x566 (Girth 3016 x 702) | CSS-P2-PG1 | PG1-75 | West | (L7-10) | 4 | Grey: 56B0/4850 | Outside | Y | 17.1496 | 68.5983 | 2855 | 566 | 4 | 6.4637 | 3016 | 702 | 4 | 8.4689 | m2 | 3 | 0 | 4
58 | PR2306 (SO-777) | Chapel Street | Panel PG1-76 451x978 (Girth 612 x 1114) | CSS-P2-PG1 | PG1-76 | West | (L7-10) | 4 | Grey: 56B0/4850 | Outside | Y | 5.5223 | 22.0893 | 451 | 978 | 4 | 1.7643 | 612 | 1114 | 4 | 2.7271 | m2 | 3 | 0 | 4
59 | PR2306 (SO-777) | Chapel Street | Stiffener PG1-76 50x978 (Girth 198 x 978) | CSS-P2-PG1 | PG1-76 | West | (L7-10) | 4 | Mill Finish | Outside | Y | 1.5685 | 6.2741 | 50 | 978 | 4 | 0.1956 | 198 | 978 | 4 | 0.77458 | m2 | 3 | 0 | 4
60 | PR2306 (SO-777) | Chapel Street | Panel PG1-75 2855x566 (Girth 3016 x 702) | CSS-P3-PG1 | PG1-75 | West | (L11-16) | 2 | Grey: 56B0/4850 | Outside | Y | 17.1496 | 34.2992 | 2855 | 566 | 2 | 3.2319 | 3016 | 702 | 2 | 4.2345 | m2 | 3 | 0 | 2
61 | PR2306 (SO-777) | Chapel Street | Panel PG1-76 451x978 (Girth 612 x 1114) | CSS-P3-PG1 | PG1-76 | West | (L11-16) | 3 | Grey: 56B0/4850 | Outside | Y | 5.5223 | 16.567 | 451 | 978 | 3 | 1.3232 | 612 | 1114 | 3 | 2.0453 | m2 | 3 | 0 | 3
62 | PR2306 (SO-777) | Chapel Street | Stiffener PG1-76 50x978 (Girth 198 x 978) | CSS-P3-PG1 | PG1-76 | West | (L11-16) | 3 | Mill Finish | Outside | Y | 1.5685 | 4.7055 | 50 | 978 | 3 | 0.1467 | 198 | 978 | 3 | 0.58093 | m2 | 3 | 0 | 3
63 | PR2306 (SO-777) | Chapel Street | Panel PG1-77 465x978 (Girth 626 x 1114) | CSS-P3-PG1 | PG1-77 | West | (L11-16) | 1 | Grey: 56B0/4850 | Outside | Y | 5.6486 | 5.6486 | 465 | 978 | 1 | 0.45477 | 626 | 1114 | 1 | 0.69736 | m2 | 3 | 0 | 1
64 | PR2306 (SO-777) | Chapel Street | Stiffener PG1-77 50x978 (Girth 198 x 978) | CSS-P3-PG1 | PG1-77 | West | (L11-16) | 1 | Mill Finish | Outside | Y | 1.5685 | 1.5685 | 50 | 978 | 1 | 0.0489 | 198 | 978 | 1 | 0.19364 | m2 | 3 | 0 | 1
65 | PR2306 (SO-777) | Chapel Street | Pressing (LH Jamb) PS01-A 45x2413 (Girth 596 x 2413) | CSS-P1-PS01 | PS01-A | South | (L2-6) | 10 | Bronze: 56PRR/4163 | Outside | B | 11.649 | 116.49 | 45 | 2413 | 10 | 1.0858 | 596 | 2413 | 10 | 14.3815 | m2 | 3 | 0 | 45
66 | PR2306 (SO-777) | Chapel Street | End Cap PS01-A 45x147 (Girth 45 x 147) | CSS-P1-PS01 | PS01-A | South | (L2-6) | 10 | Bronze: 56PRR/4163 | Outside | B | 0.053582 | 0.53582 | 45 | 147 | 10 | 0.06615 | 45 | 147 | 10 | 0.06615 | m2 | 3 | 3.39 | 45
67 | PR2306 (SO-777) | Chapel Street | Angle 25x50 PS01-A 50x50 (Girth 75 x 50) | CSS-P1-PS01 | PS01-A | South | (L2-6) | 10 | Mill Finish | NA | B | 0.030375 | 0.30375 | 50 | 50 | 10 | 0.025 | 75 | 50 | 10 | 0.0375 | m2 | 3 | 0 | 45
68 | PR2306 (SO-777) | Chapel Street | Pressing (LH Jamb) PS01-A 45x2413 (Girth 596 x 2413) | CSS-P2-PS01 | PS01-A | South | (L7-10) | 8 | Bronze: 56PRR/4163 | Outside | B | 11.649 | 93.192 | 45 | 2413 | 8 | 0.86868 | 596 | 2413 | 8 | 11.5052 | m2 | 3 | 0 | 36
69 | PR2306 (SO-777) | Chapel Street | End Cap PS01-A 45x147 (Girth 45 x 147) | CSS-P2-PS01 | PS01-A | South | (L7-10) | 8 | Bronze: 56PRR/4163 | Outside | B | 0.053582 | 0.42865 | 45 | 147 | 8 | 0.05292 | 45 | 147 | 8 | 0.05292 | m2 | 3 | 2.712 | 36
70 | PR2306 (SO-777) | Chapel Street | Angle 25x50 PS01-A 50x50 (Girth 75 x 50) | CSS-P2-PS01 | PS01-A | South | (L7-10) | 8 | Mill Finish | NA | B | 0.030375 | 0.243 | 50 | 50 | 8 | 0.02 | 75 | 50 | 8 | 0.03 | m2 | 3 | 0 | 36
71 | PR2306 (SO-777) | Chapel Street | Pressing (LH Jamb) PS01-A 45x2413 (Girth 596 x 2413) | CSS-P3-PS01 | PS01-A | South | (L11-16) | 4 | Bronze: 56PRR/4163 | Outside | B | 11.649 | 46.596 | 45 | 2413 | 4 | 0.43434 | 596 | 2413 | 4 | 5.7526 | m2 | 3 | 0 | 36
72 | PR2306 (SO-777) | Chapel Street | End Cap PS01-A 45x147 (Girth 45 x 147) | CSS-P3-PS01 | PS01-A | South | (L11-16) | 4 | Bronze: 56PRR/4163 | Outside | B | 0.053582 | 0.21433 | 45 | 147 | 4 | 0.02646 | 45 | 147 | 4 | 0.02646 | m2 | 3 | 1.356 | 36
73 | PR2306 (SO-777) | Chapel Street | Angle 25x50 PS01-A 50x50 (Girth 75 x 50) | CSS-P3-PS01 | PS01-A | South | (L11-16) | 4 | Mill Finish | NA | B | 0.030375 | 0.1215 | 50 | 50 | 4 | 0.01 | 75 | 50 | 4 | 0.015 | m2 | 3 | 0 | 36
74 | PR2306 (SO-777) | Chapel Street | Pressing (RH Jamb) PS02-A 45x2413 (Girth 602 x 2413) | CSS-P1-PS02 | PS02-A | South | (L2-6) | 10 | Bronze: 56PRR/4163 | Outside | C | 11.7663 | 117.6627 | 45 | 2413 | 10 | 1.0858 | 602 | 2413 | 10 | 14.5263 | m2 | 3 | 0 | 45
75 | PR2306 (SO-777) | Chapel Street | End Cap PS02-A 45x150 (Girth 45 x 150) | CSS-P1-PS02 | PS02-A | South | (L2-6) | 10 | Bronze: 56PRR/4163 | Outside | C | 0.054675 | 0.54675 | 45 | 150 | 10 | 0.0675 | 45 | 150 | 10 | 0.0675 | m2 | 3 | 3.45 | 45
76 | PR2306 (SO-777) | Chapel Street | Angle 25x50 PS02-A 50x50 (Girth 75 x 50) | CSS-P1-PS02 | PS02-A | South | (L2-6) | 10 | Mill Finish | NA | C | 0.030375 | 0.30375 | 50 | 50 | 10 | 0.025 | 75 | 50 | 10 | 0.0375 | m2 | 3 | 0 | 45
77 | PR2306 (SO-777) | Chapel Street | Pressing (RH Jamb) PS02-A 45x2413 (Girth 602 x 2413) | CSS-P2-PS02 | PS02-A | South | (L7-10) | 8 | Bronze: 56PRR/4163 | Outside | C | 11.7663 | 94.1302 | 45 | 2413 | 8 | 0.86868 | 602 | 2413 | 8 | 11.621 | m2 | 3 | 0 | 36
78 | PR2306 (SO-777) | Chapel Street | End Cap PS02-A 45x150 (Girth 45 x 150) | CSS-P2-PS02 | PS02-A | South | (L7-10) | 8 | Bronze: 56PRR/4163 | Outside | C | 0.054675 | 0.4374 | 45 | 150 | 8 | 0.054 | 45 | 150 | 8 | 0.054 | m2 | 3 | 2.76 | 36
79 | PR2306 (SO-777) | Chapel Street | Angle 25x50 PS02-A 50x50 (Girth 75 x 50) | CSS-P2-PS02 | PS02-A | South | (L7-10) | 8 | Mill Finish | NA | C | 0.030375 | 0.243 | 50 | 50 | 8 | 0.02 | 75 | 50 | 8 | 0.03 | m2 | 3 | 0 | 36
80 | PR2306 (SO-777) | Chapel Street | Pressing (RH Jamb) PS02-A 45x2413 (Girth 602 x 2413) | CSS-P3-PS02 | PS02-A | South | (L11-16) | 4 | Bronze: 56PRR/4163 | Outside | C | 11.7663 | 47.0651 | 45 | 2413 | 4 | 0.43434 | 602 | 2413 | 4 | 5.8105 | m2 | 3 | 0 | 35
81 | PR2306 (SO-777) | Chapel Street | End Cap PS02-A 45x150 (Girth 45 x 150) | CSS-P3-PS02 | PS02-A | South | (L11-16) | 4 | Bronze: 56PRR/4163 | Outside | C | 0.054675 | 0.2187 | 45 | 150 | 4 | 0.027 | 45 | 150 | 4 | 0.027 | m2 | 3 | 1.38 | 35
82 | PR2306 (SO-777) | Chapel Street | Angle 25x50 PS02-A 50x50 (Girth 75 x 50) | CSS-P3-PS02 | PS02-A | South | (L11-16) | 4 | Mill Finish | NA | C | 0.030375 | 0.1215 | 50 | 50 | 4 | 0.01 | 75 | 50 | 4 | 0.015 | m2 | 3 | 0 | 35
83 | PR2306 (SO-777) | Chapel Street | Pressing (Cill) PS03-A 45x1015 (Girth 563 x 1015) | CSS-P1-PS03 | PS03-A | South | (L2-6) | 10 | Bronze: 56PRR/4163 | Outside | D | 4.6287 | 46.287 | 45 | 1015 | 10 | 0.45675 | 563 | 1015 | 10 | 5.7145 | m2 | 3 | 0 | 45
84 | PR2306 (SO-777) | Chapel Street | Pressing (Cill) PS03-A 45x1015 (Girth 563 x 1015) | CSS-P2-PS03 | PS03-A | South | (L7-10) | 8 | Bronze: 56PRR/4163 | Outside | D | 4.6287 | 37.0296 | 45 | 1015 | 8 | 0.3654 | 563 | 1015 | 8 | 4.5716 | m2 | 3 | 0 | 36
85 | PR2306 (SO-777) | Chapel Street | Pressing (Cill) PS03-A 45x1015 (Girth 563 x 1015) | CSS-P3-PS03 | PS03-A | South | (L11-16) | 4 | Bronze: 56PRR/4163 | Outside | D | 4.6287 | 18.5148 | 45 | 1015 | 4 | 0.1827 | 563 | 1015 | 4 | 2.2858 | m2 | 3 | 0 | 35
86 | PR2306 (SO-777) | Chapel Street | Pressing (Head) PS04-A 45x1105 (Girth 630 x 1105) | CSS-P1-PS04 | PS04-A | South | (L2-6) | 10 | Bronze: 56PRR/4163 | Outside | E | 5.6388 | 56.3882 | 45 | 1105 | 10 | 0.49725 | 630 | 1105 | 10 | 6.9615 | m2 | 3 | 0 | 45
87 | PR2306 (SO-777) | Chapel Street | End Cap PS04-A 45x150 (Girth 45 x 150) | CSS-P1-PS04 | PS04-A | South | (L2-6) | 20 | Bronze: 56PRR/4163 | Outside | E | 0.054675 | 1.0935 | 45 | 150 | 20 | 0.135 | 45 | 150 | 20 | 0.135 | m2 | 3 | 6.9 | 90
88 | PR2306 (SO-777) | Chapel Street | Pressing (Head) PS04-A 45x1105 (Girth 630 x 1105) | CSS-P2-PS04 | PS04-A | South | (L7-10) | 8 | Bronze: 56PRR/4163 | Outside | E | 5.6388 | 45.1105 | 45 | 1105 | 8 | 0.3978 | 630 | 1105 | 8 | 5.5692 | m2 | 3 | 0 | 36
89 | PR2306 (SO-777) | Chapel Street | End Cap PS04-A 45x150 (Girth 45 x 150) | CSS-P2-PS04 | PS04-A | South | (L7-10) | 16 | Bronze: 56PRR/4163 | Outside | E | 0.054675 | 0.8748 | 45 | 150 | 16 | 0.108 | 45 | 150 | 16 | 0.108 | m2 | 3 | 5.52 | 72
90 | PR2306 (SO-777) | Chapel Street | Pressing (Head) PS04-A 45x1105 (Girth 630 x 1105) | CSS-P3-PS04 | PS04-A | South | (L7-10) | 4 | Bronze: 56PRR/4163 | Outside | E | 5.6388 | 22.5553 | 45 | 1105 | 4 | 0.1989 | 630 | 1105 | 4 | 2.7846 | m2 | 3 | 0 | 35
91 | PR2306 (SO-777) | Chapel Street | End Cap PS04-A 45x150 (Girth 45 x 150) | CSS-P3-PS04 | PS04-A | South | (L7-10) | 8 | Bronze: 56PRR/4163 | Outside | E | 0.054675 | 0.4374 | 45 | 150 | 8 | 0.054 | 45 | 150 | 8 | 0.054 | m2 | 3 | 2.76 | 70
92 | PR2306 (SO-777) | Chapel Street | Angle 25x25 PS13-A-1 25x2368 (Girth 50 x 2368) | CSS-P1-PS13 | PS13-A-1 | South | (L2-6) | 44 | Bronze: 56PRR/4163 | Outside | I | 0.47952 | 21.0989 | 25 | 2368 | 44 | 2.6048 | 50 | 2368 | 44 | 5.2096 | m2 | 1.5 | 0 | 90
93 | PR2306 (SO-777) | Chapel Street | Angle 25x25 PS13-A-2 25x1074 (Girth 50 x 1074) | CSS-P1-PS13 | PS13-A-2 | South | (L2-6) | 22 | Bronze: 56PRR/4163 | Outside | I | 0.21749 | 4.7847 | 25 | 1074 | 22 | 0.5907 | 50 | 1074 | 22 | 1.1814 | m2 | 1.5 | 0 | 45
94 | PR2306 (SO-777) | Chapel Street | Angle 30x30 PS14-A-1 30x1013 (Girth 60 x 1013) | CSS-P1-PS14 | PS14-A-1 | South | (L2-6) | 22 | Bronze: 56PRR/4163 | Outside | H | 0.32821 | 7.2207 | 30 | 1013 | 22 | 0.66858 | 60 | 1013 | 22 | 1.3372 | m2 | 2 | 0 | 45
95 | PR2306 (SO-777) | Chapel Street | Angle 25x25 PS13-I-1 25x2328 (Girth 50 x 2328) | CSS-P1-PS15 | PS15-I.1-1 | West | (L2-6) | 10 | Grey: 56B0/4850 | Outside | I | 0.47142 | 4.7142 | 25 | 2373 | 10 | 0.59325 | 50 | 2328 | 10 | 1.164 | m2 | 1.5 | 0 | 10
96 | PR2306 (SO-777) | Chapel Street | Angle 25x25 PS13-I-2 25x972 (Girth 50 x 972) | CSS-P1-PS15 | PS15-I.1-2 | West | (L2-6) | 5 | Grey: 56B0/4850 | Outside | I | 0.19683 | 0.98415 | 25 | 978 | 5 | 0.12225 | 50 | 972 | 5 | 0.243 | m2 | 1.5 | 0 | 5
97 | PR2306 (SO-777) | Chapel Street | Angle 25x25 PS13-I-1 25x2328 (Girth 50 x 2328) | CSS-P2-PS15 | PS15-I.1-1 | West | (L7-10) | 8 | Grey: 56B0/4850 | Outside | I | 0.47142 | 3.7714 | 25 | 2373 | 8 | 0.4746 | 50 | 2328 | 8 | 0.9312 | m2 | 1.5 | 0 | 8
98 | PR2306 (SO-777) | Chapel Street | Angle 25x25 PS13-I-2 25x972 (Girth 50 x 972) | CSS-P2-PS15 | PS15-I.1-2 | West | (L7-10) | 4 | Grey: 56B0/4850 | Outside | I | 0.19683 | 0.78732 | 25 | 978 | 4 | 0.0978 | 50 | 972 | 4 | 0.1944 | m2 | 1.5 | 0 | 4
99 | PR2306 (SO-777) | Chapel Street | Angle 25x25 PS13-I-1 25x2328 (Girth 50 x 2328) | CSS-P3-PS15 | PS15-I.1-1 | West | (L11-16) | 6 | Grey: 56B0/4850 | Outside | I | 0.47142 | 2.8285 | 25 | 2373 | 6 | 0.35595 | 50 | 2328 | 6 | 0.6984 | m2 | 1.5 | 0 | 6
100 | PR2306 (SO-777) | Chapel Street | Angle 25x25 PS13-I-2 25x972 (Girth 50 x 972) | CSS-P3-PS15 | PS15-I.1-2 | West | (L11-16) | 3 | Grey: 56B0/4850 | Outside | I | 0.19683 | 0.59049 | 25 | 978 | 3 | 0.07335 | 50 | 972 | 3 | 0.1458 | m2 | 1.5 | 0 | 3
101 | PR2306 (SO-777) | Chapel Street | Angle 30x30 PS15-I.1-2 30x954 (Girth 60 x 954) | CSS-P1-PS16 | PS15-I.1-2 | West | (L2-6) | 5 | Grey: 56B0/4850 | Outside | G | 0.46364 | 2.3182 | 30 | 954 | 5 | 0.1431 | 60 | 954 | 5 | 0.2862 | m2 | 3 | 0 | 5
102 | PR2306 (SO-777) | Chapel Street | Angle 30x30 PS15-I.1-2 30x954 (Girth 60 x 954) | CSS-P2-PS16 | PS15-I.1-2 | West | (L7-10) | 4 | Grey: 56B0/4850 | Outside | G | 0.46364 | 1.8546 | 30 | 954 | 4 | 0.11448 | 60 | 954 | 4 | 0.22896 | m2 | 3 | 0 | 4
103 | PR2306 (SO-777) | Chapel Street | Angle 30x30 PS15-I.1-2 30x954 (Girth 60 x 954) | CSS-P3-PS16 | PS15-I.1-2 | West | (L11-16) | 3 | Grey: 56B0/4850 | Outside | G | 0.46364 | 1.3909 | 30 | 954 | 3 | 85860 | 60 | 954 | 3 | 0.17172 | m2 | 3 | 0 | 3
[8 empty] | 938 | [7 empty] | 938 | 86275.5555 |  |  | 938 | 658.3284